## backlog
ID | Pred. | Milestone | Title | AS A ... | I WANT TO ... | SO THAT ... | Acceptance Criteria | Tasks | Required data | Skills level | Value | Cost | Priority
1 |  | MVP | Update privacy notice | Website visitor | Be informed of personal data processings | I can be sure that my personal data privacy rights are respected | GIVEN I am a website visitor on the Privacy Notice page WHEN I search for personal data proecssings and 3rd party processors THEN I find the required legal information | Frontend - add required legal information to the Privacy Notice page | - DPO contact - types of data processed - lawful basis for processing personal data - 3rd party data processors (location and privacy policies) | - junior frontend developer | 8 - Must have | 1 - S | 8
2 |  | MVP | Update privacy settings | Authenticated user | Change my consent to process my personal data | I can be sure that my personal data privacy rights are respected | GIVEN I am a authenticated user on the Privacy Settings page WHEN I consent to the processing of my personal data (profile informations and submitted photos) THEN I have access to the Personal Recommendations feature --- GIVEN I am a authenticated user on the Privacy Settings page WHEN I DO NOT consent to the processing of my personal data (profile informations and submitted photos) THEN I DO NOT have access to the Personal Recommendations feature AND my personal data (profile informations and submitted photos) are deleted | Frontend - add a "consent" toggle button to the Privacy Settings page - add a confirmation step when toggle OFF (personal data will be deleted) Backend - implement API POST /user/{user_id} : "personal_recommendations_consent" = True / False - if False => delete {user_id} personal data (profile informations and submitted photos) Database - add a "personal_recommendations_consent" (bool) column to the user table | - consent to processing of personal data to deliver relevant recommendations | - junior frontend developer - junior backend developer | 8 - Must have | 2 - M | 4
3 |  | MVP | Update profile settings | Authenticated user | Edit my profile | I can get more relevant recommendations | GIVEN I am a authenticated user on my Profile page AND I have given my consent to the processing of my personal data WHEN I change my profile informations THEN the Personal Recommendations feature is more relevant to my tastes | Frontend - add "gender", "age", "location", "shirt/pants/shoes_sizes", "favorite_colors", "favorite_styles" fields to the user Profile page Backend - implement API POST /user/{user_id} : "gender", "age", "location", "shirt/pants/shoes_sizes", "favorite_colors", "favorite_styles" - trigger recommendation system model update for the user - get new recommendations - store new recommendations in NoSQL "user_recommendations" table Database - add a "gender", "age", "shirt/pants/shoes_sizes", "favorite_styles" columns to the user table Machine Learning - integrate user profile data into the recommendation system | User : - gender : Female / Male / Other - age : int - location : text - shirt size : XS / S / M / L / XL / XXL - pants size : 34 / 36 / 38 / 40 / 42 / 44 / 46 - shoes size : 38 / 39 / 40 / 41 / 42 / 43 / 44 / 45 / 46 - favorite colors : black / grey / white / blue / brown / red / green / yellow / pink - favorite styles : formal / casual / streetware / sportswear | - junior frontend developer - senior backend developer - middle ML engineer | 2 - Could have | 4 - L | 0.5
4 |  | MVP | Submit a photo | Authenticated user | Send a photo of an outfit I like | I can get more relevant recommendations | GIVEN I am a authenticated user on my Profile page AND I have given my consent to the processing of my personal data WHEN I add a photo of an outfit I like THEN the Personal Recommendations feature is more relevant to my tastes | Frontend - create a "Outfits I like" page - add a "New outfit" form : "outfit_photo" upload field - display all uploaded outfit photos in a grid Backend - implement API PUT /user/{user_id}/outfit_photo : "photo" (binary) - save the photo to disk - update the "path" attribute - trigger recommendation system model update for the user - get new recommendations - store new recommendations in NoSQL "user_recommendations" table - implement API GET /user/{user_id}/outfit_photo : return all photos (id, path) Database - create a "outfit_photo" table - add the "id" and "path" columns Machine Learning - train an clothes recognition model on existing articles photos - process the photo to recognize articles - integrate recognized articles into the recommendation system | Photo : - id : UUID - path : string - photo : binary | - middle frontend developer - senior backend developer - senior ML engineer | 8 - Must have | 8 - XL | 1
5 | 4 | MVP | Delete a photo | User with submitted photo(s) | Remove a submitted photo | I can get more relevant recommendations | GIVEN I am a authenticated user on my Profile page AND I have given my consent to the processing of my personal data WHEN I remove a photo of an outfit I don't like THEN the Personal Recommendations feature is more relevant to my tastes | Frontend - add a "Delete" button on the "Outfits" page with confirmation step Backend - implement API DELETE /outfit_photo/{outfit_photo_id} - trigger recommendation system model update for the user - get new recommendations - store new recommendations in NoSQL "user_recommendations" table Machine Learning - update the recommendation system model for the user | - submitted photo id | - junior frontend developer - senior backend developer - middle ML engineer | 4 - Should have | 4 - L | 1
6 | 3;4 | MVP | Personal recommendations | User with completed profile and submitted photo(s) | See the list of recommended articles | I can eventually purchase an article I like | GIVEN I am a authenticated user on my Personal Recommendations page AND I have updated my profile informations AND I have submitted a photo of an outfit I like WHEN I browse the recommended articles THEN the most relevant are recommended first | Frontend - create a "Personal recommendations" page - display articles Backend - implement API GET /user/{user_id}/recommendations - return articles by order of relevance given by the recommender system Database - create "user_recommendations" table in NoSQL Database : user_id -> [article_id_1, article_id_2, ...] Machine Learning - train a recommender system model with the usre profiles and submitted photos - store articles recommendations per user in the NoSQL Database |  | - middle frontend developer - junior backend developer - senior ML engineer | 8 - Must have | 8 - XL | 1
7 | 4 | V1 | Create a style | Authenticated user | Create a personal style | I can categorize different photos of outfit |  |  | Style : - title : string - description : text - relation : => N Photo Photo : - relation : => N Style |  | 4 - Should have | 4 - L | 1
8 | 7 | V1 | List my styles | User with personal style(s) | List all my styles | I can select one in particular |  |  |  |  | 4 - Should have | 2 - M | 2
9 | 7 | V1 | Edit a style | User with personal style(s) | Modify a personal style informations | I can better describe this style |  |  | - style id |  | 1 - Won't have | 1 - S | 1
10 | 7 | V1 | Delete a style | User with personal style(s) | Remove a personal style | I don't see a personal style I don't need |  |  | - style id |  | 2 - Could have | 2 - M | 1
11 | 7 | V1 | Manage a style's photos | User with style(s) and photo(s) | Detach / Attach a photo to a style | I can improve this style's recommendations |  |  | - style id - photo id |  | 4 - Should have | 2 - M | 2
12 | 7;6 | V1 | Personal style recommendations | User with personal style(s) | See the list of recommended articles for a particular style | I can eventually purchase an article I like |  |  |  |  | 4 - Should have | 2 - M | 2

## Critères INVEST
Independent → Pas de dépendance entre les User Stories.
Negotiable → La User Story peut être arbitrée par le client et l'équipe.
Valuable → Un besoin est toujours associé à la User Story.
Estimable → L’équipe doit être en capacité d'estimer la User Story.
Small → La User Story est décrite précisément.
Testable → Les critères d’acceptation de la User Story sont atteignables.

## Critères SMART
Specific → Toute votre équipe comprend ce qu’il y a à faire.
Mesurable → Votre équipe sait comment s’assurer que la tâche est réalisée.
Achievable → Votre équipe dispose de tous les moyens pour réaliser la tâche.
Relevant → La tâche participe bien à la concrétisation de la user story.
Time Bound → La tâche a une durée de travail connue et limitée.

## ref
Value | Cost
1 - Won't have | 1 - S
2 - Could have | 2 - M
4 - Should have | 4 - L
8 - Must have | 8 - XL