## Project Sizing
		BUILD					TOTAL		RUN					TOTAL
Time		Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14			Month 1	Month 2	Month 3	Month 4	Month 5	Month 6	Month 7	Month 8	Month 9	Month 10	Month 11	Month 12
Sprints		Sprint 0		Sprint 1		Sprint 2		Sprint 3		Sprint 4		Sprint 5		Sprint 6				Quarter 1			Quarter 2			Quarter 3			Quarter 4
Milestones		Kick-Off / PoC		MVP					V1					Semester 1					Semester 2
Planning	Workload (days)
Product Manager		1	1	0.5	0.5	0.5	0.5	0.5	2	0.5	0.5	0.5	0.5	0.5	2	11		0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	6
Product Owner		2	2	1	2	1	2	2	4	1	2	1	2	2	4	28		0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	6
SCRUM Master		2	2	2.5	2.5	2.5	2.5	2.5	2.5	2.5	2.5	2.5	2.5	2.5	2.5	34		1	1	1	1	1	1	1	1	1	1	1	1	12
Frontend developer		0.5	0.5	5	5	5	5	5	5	5	5	5	5	5	5	61		1	1	1	1	1	1	1	1	1	1	1	1	12
Backend developer		0.5	0.5	5	5	5	5	5	5	5	5	5	5	5	5	61		1	1	1	1	1	1	1	1	1	1	1	1	12
AI / ML / Data Engineer		5	5	0	1	2	4	5	5	5	5	5	5	5	5	57		4	4	4	4	4	4	4	4	4	4	4	4	48
QA Engineer		0.5	0.5	1	2	1	2	1	2	1	2	1	2	1	2	19		1	1	1	1	1	1	1	1	1	1	1	1	12
SRE		0.5	0.5				1	2	4	0.5	0.5	0.5	0.5	0.5	0.5	11		2	2	2	2	2	2	2	2	2	2	2	2	24
TOTAL		12	12	15	18	17	22	23	29.5	20.5	22.5	20.5	22.5	21.5	26	282		11	11	11	11	11	11	11	11	11	11	11	11	132

Investments
Human	Cost / day (€)
Product Manager	450.00 €	450 €	450 €	225 €	225 €	225 €	225 €	225 €	900 €	225 €	225 €	225 €	225 €	225 €	900 €	4,950 €		225 €	225 €	225 €	225 €	225 €	225 €	225 €	225 €	225 €	225 €	225 €	225 €	2,700 €
Product Owner	350.00 €	700 €	700 €	350 €	700 €	350 €	700 €	700 €	1,400 €	350 €	700 €	350 €	700 €	700 €	1,400 €	9,800 €		175 €	175 €	175 €	175 €	175 €	175 €	175 €	175 €	175 €	175 €	175 €	175 €	2,100 €
SCRUM Master	300.00 €	600 €	600 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	750 €	10,200 €		300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	3,600 €
Frontend developer	300.00 €	150 €	150 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	1,500 €	18,300 €		300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	3,600 €
Backend developer	350.00 €	175 €	175 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	1,750 €	21,350 €		350 €	350 €	350 €	350 €	350 €	350 €	350 €	350 €	350 €	350 €	350 €	350 €	4,200 €
AI / ML / Data Engineer	400.00 €	2,000 €	2,000 €	0 €	400 €	800 €	1,600 €	2,000 €	2,000 €	2,000 €	2,000 €	2,000 €	2,000 €	2,000 €	2,000 €	22,800 €		1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	1,600 €	19,200 €
QA Engineer	300.00 €	150 €	150 €	300 €	600 €	300 €	600 €	300 €	600 €	300 €	600 €	300 €	600 €	300 €	600 €	5,700 €		300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	300 €	3,600 €
SRE	400.00 €	200 €	200 €	0 €	0 €	0 €	400 €	800 €	1,600 €	200 €	200 €	200 €	200 €	200 €	200 €	4,400 €		800 €	800 €	800 €	800 €	800 €	800 €	800 €	800 €	800 €	800 €	800 €	800 €	9,600 €
TOTAL		4,425 €	4,425 €	4,875 €	5,925 €	5,675 €	7,525 €	8,025 €	10,500 €	7,075 €	7,725 €	7,075 €	7,725 €	7,425 €	9,100 €	97,500 €		4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	4,050 €	48,600 €

Infrastructure
Usage
# of articles		1000	1000	1000	1000	1000	1000	1000	1000	1000	1000	1000	1000	1000	1000			1000	1020	1040	1061	1082	1104	1126	1149	1172	1195	1219	1243
# of photos per articles		10	10	10	10	10	10	10	10	10	10	10	10	10	10			10	10	10	10	10	10	10	10	10	10	10	10
# of Personal Style feature users		0	0	0	0	0	0	0	0	100	200	500	1000	2000	5000			10000	10500	11025	11576	12155	12763	13401	14071	14775	15513	16289	17103
# of Personal Styles per user					1	1	1	1	1	1			1	1	2	2	2	2	3	3	3	3	3	3
# of photo per Personal Style					1	2	3	4	5	6			10	10	10	10	10	10	10	10	10	10	10	10
# of model training		5	5	0	1	2	4	5	5	7	7	7	7	7	7			30	30	30	30	30	30	30	30	30	30	30	30

Already in place
App Service Plan	Serve web app
SQL Database	Web app data
Blob Storage	Articles photos

Articles detection
Blob Storage (Standard - Hot)	Personal Style photos	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	1 €	2 €	2 €		20 €	21 €	44 €	46 €	49 €	51 €	80 €	84 €	89 €	93 €	98 €	103 €	778 €
Function	Schedule training	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €		0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €
Machine Learning (GPU)	Train : detect articles	100 €	100 €	0 €	20 €	40 €	80 €	100 €	100 €	140 €	140 €	140 €	140 €	140 €	140 €	1,380 €		600 €	612 €	624 €	637 €	649 €	662 €	676 €	689 €	703 €	717 €	731 €	746 €	8,047 €
Machine Learning	Predict : detect articles					0 €	0 €	1 €	3 €	7 €	25 €	36 €		69 €	7 €	15 €	15 €	16 €	17 €	27 €	28 €	29 €	31 €	32 €	34 €	320 €
NoSQL Database	Detected articles					0 €	0 €	0 €	0 €	0 €	1 €	1 €		10 €	11 €	22 €	23 €	24 €	26 €	40 €	42 €	44 €	47 €	49 €	51 €	389 €

Recommender
Function	Schedule training	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €		0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €	0 €
Machine Learning	Train : recommender	10 €	10 €	0 €	2 €	4 €	8 €	10 €	10 €	11 €	13 €	17 €	24 €	38 €	80 €	237 €		610 €	640 €	672 €	705 €	739 €	776 €	814 €	854 €	896 €	941 €	987 €	1,036 €	9,670 €
Machine Learning	Predict : rank articles					0 €	0 €	1 €	3 €	7 €	25 €	36 €		69 €	7 €	15 €	15 €	16 €	17 €	27 €	28 €	29 €	31 €	32 €	34 €	320 €
NoSQL Database	Ranked articles					0 €	0 €	0 €	0 €	0 €	1 €	1 €		10 €	11 €	22 €	23 €	24 €	26 €	40 €	42 €	44 €	47 €	49 €	51 €	389 €

TOTAL		110 €	110 €	0 €	22 €	44 €	88 €	110 €	110 €	152 €	153 €	160 €	170 €	193 €	273 €	1,695 €		1,389 €	1,308 €	1,413 €	1,465 €	1,518 €	1,574 €	1,704 €	1,768 €	1,835 €	1,906 €	1,979 €	2,055 €	19,914 €

TOTAL Investments		4,535 €	4,535 €	4,875 €	5,947 €	5,719 €	7,613 €	8,135 €	10,610 €	7,227 €	7,878 €	7,235 €	7,895 €	7,618 €	9,373 €	99,195 €		5,439 €	5,358 €	5,463 €	5,515 €	5,568 €	5,624 €	5,754 €	5,818 €	5,885 €	5,956 €	6,029 €	6,105 €	68,514 €

Returns
Comercial data
Base Value per sale	20 €
Base Margin per sale	20%
Base profits					100 €	200 €	500 €	1,000 €	2,000 €	5,000 €	8,800 €		40,000 €	42,000 €	44,100 €	46,305 €	48,620 €	51,051 €	53,604 €	56,284 €	59,098 €	62,053 €	65,156 €	68,414 €	636,685 €

Scenario 1
Feature impact : Value increase	15%
Feature impact : Margin increase	10%
Added Profits with Personal Styles					27 €	53 €	133 €	265 €	530 €	1,325 €	2,332 €		10,600 €	11,130 €	11,687 €	12,271 €	12,884 €	13,529 €	14,205 €	14,915 €	15,661 €	16,444 €	17,266 €	18,130 €	168,722 €
Treasury		-4,535 €	-9,070 €	-13,945 €	-19,892 €	-25,611 €	-33,224 €	-41,359 €	-51,969 €	-59,169 €	-66,995 €	-74,097 €	-81,727 €	-88,815 €	-96,863 €	-96,863 €		-91,701 €	-85,929 €	-79,706 €	-72,950 €	-65,633 €	-57,729 €	-49,278 €	-40,181 €	-30,405 €	-19,916 €	-8,679 €	3,345 €	3,345 €
ROI 1					-97.65%					1.99%

Scenario 2
Feature impact : Value increase	25%
Feature impact : Margin increase	15%
Added Profits with Personal Styles					44 €	88 €	219 €	438 €	875 €	2,188 €	3,850 €		17,500 €	18,375 €	19,294 €	20,258 €	21,271 €	22,335 €	23,452 €	24,624 €	25,855 €	27,148 €	28,506 €	29,931 €	278,550 €
Treasury		-4,535 €	-9,070 €	-13,945 €	-19,892 €	-25,611 €	-33,224 €	-41,359 €	-51,969 €	-59,152 €	-66,943 €	-73,959 €	-81,416 €	-88,159 €	-95,345 €	-95,345 €		-83,283 €	-70,266 €	-56,436 €	-41,692 €	-25,989 €	-9,278 €	8,420 €	27,226 €	47,196 €	68,389 €	90,866 €	114,691 €	114,691 €
ROI 2					-96.12%					68.39%

		Time / Treasury					Time / Treasury

## Project Risks
ID	Category	Risk	Title	Description	Owner	Impacts	Threats	Sources	Prevention measures	Mitigation measures	Likelihood	Severity	Criticity
1	Scope	Feature does not satisfy user needs	Wrong scope	Users don't use the feature because they don't need it	Product Owner	- less feature usage => lower returns / - users insatisfaction => less new and returning users	- users do not need this feature / - users are not used to this kind of feature	- users try to use the feature	- user research during first Sprint	- users feedback/satisfaction form	2	4	8
2	Quality	Feature not implemented as expected by the user	Bad UX	Users don't like the feature because it does not work as they expect	UX Designer	- confused users => less feature usage and more customer support	- users do not understand how the feature works	- users try to use the feature	- A/B testing	- feature usage monitoring	1	4	4
3	Quality	Feature not usable because of low performances	Low performances	Users complain about latency, lag or slow results	Tech Lead	- low percieved quality => less new and returning users	- users find the feature slow	- users try to use the feature	- performance testing	- profiling => code optimization and/or infrastructure resources increase	2	4	8
4	Quality	Feature not usable because of low accuracy	Low accuracy	Users complain about bad recommendations	AI Engineer	- low percieved quality => less new and returning users	- users find the feature useless	- users try to use the feature	- recommendation system evaluation	- re-train recommender system	4	4	16
5	Budget	Under-estimated human costs	Greater human costs	The actual salary of contributors is much higher than estimated	Product Manager	- increased costs	- job market salaries are higher than expected	- contributors are hired / allocated to the project	- salaries benchmarking before kick-off	- re-negotiate project budget / - use less paid (less skilled / more junior) contributors	1	2	2
6	Budget	Under-estimated infrastructure costs	Greater infrastructure costs	The actual cost of infrastructure usage is much higher than estimated	Tech Lead	- increased costs	- infrastructure price per usage increase / - infrastructure usage higher than expected	- developers and AI Engineer use infrastructure resources / - they don't optimize resources usage (stop unused environments)	- train tech team to resources costs optimisation	- monitor resources usage and costs	3	2	6
7	Budget	Over-estimated available budget	Lower budget	The actual available budget for the project is much lower than estimated	Product Manager	- not enough budget for the full project	- available budget is lower than estimated	- project budget allocation	- ask for available budget in advance	- reduce project scope	1	3	3
8	Planning	Under-estimated specification time	Delayed specifications	The time required to produce specification is much higher than estimated	Product Owner	- slows the production chain => delays product delivery => stretches project planning => increases costs	- product owner needs more time than estimated	- product owner prepares user stories		- identify and fix causes of slowness (kaizen)	2	3	6
9	Planning	Under-estimated feature development time	Delayed feature development	The time required to develop the feature is much higher than estimated	Tech Lead	- slows the production chain => delays product delivery => stretches project planning => increases costs	- developers needs more time than estimated	- developers develop user stories		- identify and fix causes of slowness (kaizen)	3	2	6
10	Planning	Under-estimated ML development time	Delayed ML development	The time required to train and optimize the ML models is much higher than estimated	AI Engineer	- slows the production chain => delays product delivery => stretches project planning => increases costs	- AI Engineer needs more time than estimated / - data acquisition / cleaning is more complex than expected / - model training / optimization is more complex than expected	- AI Engineers develop user stories		- identify and fix causes of slowness (kaizen)	4	2	8
11	Planning	Under-estimated validation time	Delayed validation	The time required to test and validate the feature is much higher than estimated	QA Engineer	- slows the production chain => delays product delivery => stretches project planning => increases costs	- QA Engineer needs more time than estimated	- QA Engineers test user stories		- identify and fix causes of slowness (kaizen)	1	1	1
12	Planning	Over-estimated available time	Premature deadline	The actual deadline of the project is much sooner than estimated	Product Manager	- not enough time for the full project	- available budget is lower than estimated	- project planning	- ask for compagny deadlines in advance	- reduce project scope	1	3	3
13	Team	Required skills are not available	Unavailable human resources	Persons with the required skills are not all available	Product Manager	- planning stretches => higher cost / - contributors don't have the required skills => lower quality	- contributors with required skills are not available according to the planning	- project planning and human resouces allocation	- book required resources in advance	- reduce project scope / - re-negotiate project budget and/or planning	3	4	12
14	Complexity	Identifying items in photos is harder than expected	Items identification dificulties	Developing the items recognition engine requires more resources (time, data, budget) and/or skills than estimated	AI Engineer	- planning stretches => higher cost / - more infrastructure usage => higher cost / - bad items detection accuracy => lower quality	- ML model is hard to train / optimize / - not enough training data / - bad quality training data	- AI Engineers develops items detection system	- proof of concept during first Sprint		4	4	16
15	Complexity	Making relevant recommendations is harder than expected	Recommendations dificulties	Developing the items recommendation engine requires more resources (time, data, budget) and/or skills than estimated	AI Engineer	- planning stretches => higher cost / - more infrastructure usage => higher cost / - bad recommender system accuracy => lower quality	- ML model is hard to train / optimize / - not enough training data / - bad quality training data	- AI Engineers develop recommender system	- proof of concept during first Sprint		4	4	16
16	Innovation	Integration of AI components is a first	Never done before	Since this project is the first of its kind, there is no prior knowledge ("expect the unexpected")	Product Manager	- unknown risks => high uncertainty => planning/budget/scope drift	- unknown risk	- during all the project	- integrate some margin in estimations		3	3	9
17	Compliance (PIA)	DPO and organisation manager are not defined	Undefined representatives	DPO and organisation manager must be defined	Product Manager	- not-compliant product => legal risk (> 10M€)	- record of data processing is not conform	- in case of control (CNIL / GPDP)	- identify DPO and organisation representative		2	4	8
18	Compliance (PIA)	Illegitimate access to data	Illegitimate access to data	An unauthorized entity has access to users personal data (Profile informations and/or Personal Style photos)	SRE	Profiling of data subject	- Access to the Database / - Access to the Blob Storage / - Man-in-the-Middle / - User credentials theft	Internal human, External human, Technical incident	- SSL Encrypted communications / - Software security audits and pentests / - Cloud : Role Based Access Control (RBAC) / - Software : Role Based Access Control (RBAC) / - Blur faces / - Data access and modification Traceability		2	3	6
19	Compliance (PIA)	Unwanted modification of data	Unwanted modification of data	An unauthorized entity alters users personal data (Profile informations and/or Personal Style photos)	SRE	Unusable Recommendations feature	- Access to the Database / - Access to the Blob Storage / - Man-in-the-Middle / - User credentials theft	Internal human, External human, Technical incident	- SSL Encrypted communications / - Software security audits and pentests / - Cloud : Role Based Access Control (RBAC) / - Software : Role Based Access Control (RBAC) / - Backup and restore / - Data access and modification Traceability		2	2	4
20	Compliance (PIA)	Data disappearance	Data disappearance	An unauthorized entity removes users personal data (Profile informations and/or Personal Style photos)	SRE	Unusable Recommendations feature	- Access to the Database / - Access to the Blob Storage / - Unavailable services / - User credentials theft	Internal human, External human, Technical incident	- SSL Encrypted communications / - Software security audits and pentests / - Cloud : Role Based Access Control (RBAC) / - Software : Role Based Access Control (RBAC) / - Backup and restore / - Data access and modification Traceability		2	2	4

ACTION PLAN
Status	Owner	Action
TODO	AI Engineer	- proof of concept during first Sprint
TODO	AI Engineer	- recommendation system evaluation
TODO	Product Manager	- book required resources in advance
DONE	Product Manager	- integrate some margin in estimations
TODO	Product Owner	- user research during first Sprint
TODO	Tech Lead	- performance testing
TODO	Product Manager	- identify DPO and organisation representative

Privacy Impact Assessment (PIA)

## Processing List
Contact details	First Name	Last Name	Email Address	Phone Number	Postal Address
Responsible for the organisation	To Be Defined (TBD)	TBD	TBD	TBD	TBD
Representative	TBD	TBD	TBD	TBD	TBD
Data Protection Officer (DPO)	TBD	TBD	TBD	TBD	TBD

Processing operation	N° / REF	Date of creation of the record form	Last update of the record form	Purpose of the data processing	Special categories of personal data?
Already in place
Authentication	1
Items search	2
Items in shopping cart	3
Purchase	4
Delivery	5
Satisfaction	6

New
Profile settings	7	11/07/2022	11/07/2022	- Store user profile informations / - Filter relevant items (matching profile criteria) / - Improve items recommendations (content-based filtering)	No
Personal Style photos	8	11/07/2022	11/07/2022	- Store users Personal Styles photos / - Identify relevant items (similar to those in the photo) / - Improve items recommendations (content-based filtering)	No
Recommender System	9	12/07/2022	12/07/2022	- Produce and store items recommendations / based on user Profile informations and Personal Style photos	No

## Data Processing #7 - Profile settings
Description of the processing operation
Name of the processing operation	Profile settings
N° / REF	7
Data of creation of the processing	11/07/2022
Update of the processing	11/07/2022

Stakeholders	Name	Address	ZIP Code	Town	Country	Phone number	Email address
Controller	TBD	TBD	TBD	TBD	TBD	TBD	TBD
Data protection officer	TBD	TBD	TBD	TBD	TBD	TBD	TBD
DPO's Organisation (if external DPO)	N/A
Representative	N/A
Joint controller(s)	N/A

Purpose(s) of the data processing
Main purpose	Improve items recommendation
Sub-purpose 1	Filter relevant items
Sub-purpose 2	Store user profile informations
Sub-purpose 3	Software debugging

Categories of personal data	Description					Data retention period
Marital status, ID, identification data, images...	N/A
Personal life (lifestyle, family situation, etc.)	gender, age, shirt size, pants size, shoes size, favorite colors, favorite styles					- Actual data : While consented / - Backups : 2 weeks
Economic and financial information (income, financial situation, tax situation, etc.)	N/A
Connection data (IP address, logs, etc.)	N/A
Location data (movements, GPS data, GSM, etc.)	location					- Actual data : While consented / - Backups : 2 weeks
Social Security Number (or NIR)	N/A

Special categories of personal data	Description					Data retention period
Data revealing racial or ethnic origin	N/A
Data revealing political opinions	N/A
Data revealing religious or philosophical beliefs	N/A
Data revealing trade union membership	N/A
Genetic data	N/A
Biometric data for the purpose of uniquely identifying a natural person	N/A
Data concerning health	N/A
Data concerning a natural person's sex life or sexual orientation	N/A
Data relating to criminal convictions and offences	N/A

Categories of data subjects	Description				Details
Category 1	Authenticated users				Any user who has created an account and given their consent

Recipients	Type of recipient				Details
Recipient 1	Internal - Software Engineering team				(Write) To store the data in the database / (Read) To debug the web application
Recipient 2	External - Cloud Service Provider				To host the database

Security measures	Type of security measure				Details
Security measure 1	Software : Role Based Access Control (RBAC)				Only the user can edit its profile data
Security measure 2	Cloud : Role Based Access Control (RBAC)				Only authorized internal personnel has access to the users profile data
Security measure 3	Software security audits and pentests				The system is audited and pentested at least once per year
Security measure 4	SSL Encrypted communications				Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel
Security measure 5	Backup & restore				Daily backups stored for 2 weeks.
Security measure 6	Data access and modification Traceability				Every access to and modification of data is logged : / - timestamp / - author_id / - data_id : table_column / - origin : API endpoint used / - action : READ/WRITE/DELETE / - new_value (if action = WRITE)

Transfers to third countries or international organisations	Recipient		Country		Type of guarantees		Links to relevant documents
Recipient organisation 1	Microsoft Azure - West Europe		Netherlands		Data residency in Azure		Data Protection Resources

## Data Processing #8 - Personal Style photos
Description of the processing operation
Name of the processing operation	Personal Style photos
N° / REF	8
Data of creation of the processing	12/07/2022
Update of the processing	12/07/2022

Stakeholders	Name	Address	ZIP Code	Town	Country	Phone number	Email address
Controller	TBD	TBD	TBD	TBD	TBD	TBD	TBD
Data protection officer	TBD	TBD	TBD	TBD	TBD	TBD	TBD
DPO's Organisation (if external DPO)	N/A
Representative	N/A
Joint controller(s)	N/A

Purpose(s) of the data processing
Main purpose	Improve items recommendation
Sub-purpose 1	Identify relevant items
Sub-purpose 2	Store user style photos and preferences
Sub-purpose 3	Software debugging

Categories of personal data	Description					Data retention period
Marital status, ID, identification data, images...	photos of people (potentially the user himself) wearing clothing items that the user likes					- Actual data : While consented / - Backups : 2 weeks
Personal life (lifestyle, family situation, etc.)	N/A
Economic and financial information (income, financial situation, tax situation, etc.)	N/A
Connection data (IP address, logs, etc.)	N/A
Location data (movements, GPS data, GSM, etc.)	N/A
Social Security Number (or NIR)	N/A

Special categories of personal data	Description					Data retention period
Data revealing racial or ethnic origin	N/A
Data revealing political opinions	N/A
Data revealing religious or philosophical beliefs	N/A
Data revealing trade union membership	N/A
Genetic data	N/A
Biometric data for the purpose of uniquely identifying a natural person	N/A
Data concerning health	N/A
Data concerning a natural person's sex life or sexual orientation	N/A
Data relating to criminal convictions and offences	N/A

Categories of data subjects	Description				Details
Category 1	Authenticated users				Any user who has created an account and given their consent
Category 2	Person present in the photo				Any person who is the main subject or present in the background of the photo

Recipients	Type of recipient				Details
Recipient 1	Internal - Software Engineering team				(Write) To store the photo in the blob storage / (Read) To debug the web application
Recipient 2	External - Cloud Service Provider				To host the blob storage

Security measures	Type of security measure				Details
Security measure 1	Software : Role Based Access Control (RBAC)				Only the user can edit its Personal Style photos
Security measure 2	Cloud : Role Based Access Control (RBAC)				Only authorized internal personnel has access to the users Personal Style photos
Security measure 3	Software security audits and pentests				The system is audited and pentested at least once per year
Security measure 4	SSL Encrypted communications				Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel
Security measure 5	Backup & restore				Daily backups stored for 2 weeks.
Security measure 6	Data access and modification Traceability				Every access to and modification of data is logged : / - timestamp / - author_id / - data_id : table_column / - origin : API endpoint used / - action : READ/WRITE/DELETE / - new_value (if action = WRITE)
Security measure 7	Blur faces				Any detected face in photos will be blurred

Transfers to third countries or international organisations	Recipient		Country		Type of guarantees		Links to relevant documents
Recipient organisation 1	Microsoft Azure - West Europe		Netherlands		Data residency in Azure		Data Protection Resources

## Data Processing #9 - Recommender System
Description of the processing operation
Name of the processing operation	Recommender System
N° / REF	9
Data of creation of the processing	12/07/2022
Update of the processing	12/07/2022

Stakeholders	Name	Address	ZIP Code	Town	Country	Phone number	Email address
Controller	TBD	TBD	TBD	TBD	TBD	TBD	TBD
Data protection officer	TBD	TBD	TBD	TBD	TBD	TBD	TBD
DPO's Organisation (if external DPO)	N/A
Representative	N/A
Joint controller(s)	N/A

Purpose(s) of the data processing
Main purpose	Recommend relevant items to users given their Profile informations and Personal Style photos
Sub-purpose 1	Store recommendations in database
Sub-purpose 2	Software or recommender system debugging

Categories of personal data	Description					Data retention period
Marital status, ID, identification data, images...	User items recommendations					- While consented
Personal life (lifestyle, family situation, etc.)	N/A
Economic and financial information (income, financial situation, tax situation, etc.)	N/A
Connection data (IP address, logs, etc.)	N/A
Location data (movements, GPS data, GSM, etc.)	N/A
Social Security Number (or NIR)	N/A

Special categories of personal data	Description					Data retention period
Data revealing racial or ethnic origin	N/A
Data revealing political opinions	N/A
Data revealing religious or philosophical beliefs	N/A
Data revealing trade union membership	N/A
Genetic data	N/A
Biometric data for the purpose of uniquely identifying a natural person	N/A
Data concerning health	N/A
Data concerning a natural person's sex life or sexual orientation	N/A
Data relating to criminal convictions and offences	N/A

Categories of data subjects	Description				Details
Category 1	Authenticated users				Any user who has created an account and given their consent
Category 2	Person present in the photo				Any person who is the main subject or present in the background of the photo

Recipients	Type of recipient				Details
Recipient 1	Internal - AI Engineering team				(Read) To train the items detection system / (Read) To train the recommender system / (Read) To debug the items detection system / (Read) To debug the recommender system
Recipient 2	External - Cloud Service Provider				To host the recommender system processing units and store the recommendations

Security measures	Type of security measure				Details
Security measure 1	Software : Role Based Access Control (RBAC)				Recommendations are not editable through the software
Security measure 2	Cloud : Role Based Access Control (RBAC)				Only authorized internal personnel has access to the recommendations
Security measure 3	Software security audits and pentests				The system is audited and pentested at least once per year
Security measure 4	SSL Encrypted communications				Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel

Transfers to third countries or international organisations	Recipient		Country		Type of guarantees		Links to relevant documents
Recipient organisation 1	Microsoft Azure - West Europe		Netherlands		Data residency in Azure		Data Protection Resources