## Project Sizing
|  | BUILD | [13 empty] | TOTAL | RUN | [11 empty] | TOTAL
Time |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Sprints |  | BUILD Week 1: Sprint 0; BUILD Week 3: Sprint 1; BUILD Week 5: Sprint 2; BUILD Week 7: Sprint 3; BUILD Week 9: Sprint 4; BUILD Week 11: Sprint 5; BUILD Week 13: Sprint 6 |  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
Milestones |  | BUILD Week 1: Kick-Off / PoC; BUILD Week 3: MVP; BUILD Week 9: V1 |  | Semester 1 | [5 empty] | Semester 2
Planning | Workload (days)
Product Manager |  | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6
Product Owner |  | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 4 | 1 | 2 | 1 | 2 | 2 | 4 | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6
SCRUM Master |  | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
Frontend developer |  | 0.5 | 0.5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
Backend developer |  | 0.5 | 0.5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
AI / ML / Data Engineer |  | 5 | 5 | 0 | 1 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 57 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48
QA Engineer |  | 0.5 | 0.5 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 19 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
SRE |  | 0.5 | 0.5 |  |  |  | 1 | 2 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 11 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
TOTAL |  | 12 | 12 | 15 | 18 | 17 | 22 | 23 | 29.5 | 20.5 | 22.5 | 20.5 | 22.5 | 21.5 | 26 | 282 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 132
Investments
Human | Cost / day (€)
Product Manager | 450 | 450 | 450 | 225 | 225 | 225 | 225 | 225 | 900 | 225 | 225 | 225 | 225 | 225 | 900 | 4950 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 2700
Product Owner | 350 | 700 | 700 | 350 | 700 | 350 | 700 | 700 | 1400 | 350 | 700 | 350 | 700 | 700 | 1400 | 9800 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 2100
SCRUM Master | 300 | 600 | 600 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 10200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 3600
Frontend developer | 300 | 150 | 150 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 18300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 3600
Backend developer | 350 | 175 | 175 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 21350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 4200
AI / ML / Data Engineer | 400 | 2000 | 2000 | 0 | 400 | 800 | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 22800 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 19200
QA Engineer | 300 | 150 | 150 | 300 | 600 | 300 | 600 | 300 | 600 | 300 | 600 | 300 | 600 | 300 | 600 | 5700 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 3600
SRE | 400 | 200 | 200 | 0 | 0 | 0 | 400 | 800 | 1600 | 200 | 200 | 200 | 200 | 200 | 200 | 4400 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 9600
TOTAL |  | 4425 | 4425 | 4875 | 5925 | 5675 | 7525 | 8025 | 10500 | 7075 | 7725 | 7075 | 7725 | 7425 | 9100 | 97500 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 4050 | 48600
Infrastructure
Usage
# of articles |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 1000 | 1020 | 1040.4 | 1061.208 | 1082.4322 | 1104.0808 | 1126.1624 | 1148.6857 | 1171.6594 | 1195.0926 | 1218.9944 | 1243.3743
# of photos per articles |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
# of Personal Style feature users |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 500 | 1000 | 2000 | 5000 |  | 10000 | 10500 | 11025 | 11576.25 | 12155.0625 | 12762.8156 | 13400.9564 | 14071.0042 | 14774.5544 | 15513.2822 | 16288.9463 | 17103.3936
# of Personal Styles per user | [16 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | bar: BUILD Week 9 to BUILD Week 14
# of photo per Personal Style |  | BUILD Week 9: 1; BUILD Week 10: 2; BUILD Week 11: 3; BUILD Week 12: 4; BUILD Week 13: 5; BUILD Week 14: 6 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
# of model training |  | 5 | 5 | 0 | 1 | 2 | 4 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Already in place
App Service Plan | Serve web app
SQL Database | Web app data
Blob Storage | Articles photos
Articles detection
Blob Storage (Standard - Hot) | Personal Style photos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0.02 | 0.075 | 0.2 | 0.5 | 1.5 | 2.3 | 20 | 21 | 44.1 | 46.305 | 48.6202 | 51.0513 | 80.4057 | 84.426 | 88.6473 | 93.0797 | 97.7337 | 102.6204 | 777.9893
Function | Schedule training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Machine Learning (GPU) | Train : detect articles | 100 | 100 | 0 | 20 | 40 | 80 | 100 | 100 | 140 | 140 | 140 | 140 | 140 | 140 | 1380 | 600 | 612 | 624.24 | 636.7248 | 649.4593 | 662.4485 | 675.6975 | 689.2114 | 702.9956 | 717.0555 | 731.3967 | 746.0246 | 8047.2538
Machine Learning | Predict : detect articles | BUILD Week 9: 0.13889; BUILD Week 10: 0.27778; BUILD Week 11: 1.25; BUILD Week 12: 2.7778; BUILD Week 13: 6.9444; BUILD Week 14: 25 | 36.3889 | 69.4444 | 6.9444 | 14.5833 | 15.3125 | 16.0781 | 16.882 | 26.5892 | 27.9187 | 29.3146 | 30.7803 | 32.3193 | 33.9353 | 320.1023
NoSQL Database | Detected articles | BUILD Week 9: 0.0025; BUILD Week 10: 0.01; BUILD Week 11: 0.0375; BUILD Week 12: 0.1; BUILD Week 13: 0.25; BUILD Week 14: 0.75 | 1.15 | 10 | 10.5 | 22.05 | 23.1525 | 24.3101 | 25.5256 | 40.2029 | 42.213 | 44.3237 | 46.5398 | 48.8668 | 51.3102 | 388.9947
Recommender
Function | Schedule training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Machine Learning | Train : recommender | 10 | 10 | 0 | 2 | 4 | 8 | 10 | 10 | 11.4 | 12.8 | 17 | 24 | 38 | 80 | 237.2 | 610 | 640 | 671.5 | 704.575 | 739.3038 | 775.7689 | 814.0574 | 854.2603 | 896.4733 | 940.7969 | 987.3368 | 1036.2036 | 9670.2759
Machine Learning | Predict : rank articles | BUILD Week 9: 0.13889; BUILD Week 10: 0.27778; BUILD Week 11: 1.25; BUILD Week 12: 2.7778; BUILD Week 13: 6.9444; BUILD Week 14: 25 | 36.3889 | 69.4444 | 6.9444 | 14.5833 | 15.3125 | 16.0781 | 16.882 | 26.5892 | 27.9187 | 29.3146 | 30.7803 | 32.3193 | 33.9353 | 320.1023
NoSQL Database | Ranked articles | BUILD Week 9: 0.0025; BUILD Week 10: 0.01; BUILD Week 11: 0.0375; BUILD Week 12: 0.1; BUILD Week 13: 0.25; BUILD Week 14: 0.75 | 1.15 | 10 | 10.5 | 22.05 | 23.1525 | 24.3101 | 25.5256 | 40.2029 | 42.213 | 44.3237 | 46.5398 | 48.8668 | 51.3102 | 388.9947
TOTAL |  | 110 | 110 | 0 | 22 | 44 | 88 | 110 | 110 | 151.6878 | 153.3956 | 159.65 | 169.9556 | 192.8889 | 273 | 1694.5778 | 1388.8889 | 1307.8889 | 1413.1067 | 1464.5348 | 1518.1598 | 1574.084 | 1703.7447 | 1768.161 | 1835.3927 | 1905.5725 | 1978.8395 | 2055.3395 | 19913.713
TOTAL Investments |  | 4535 | 4535 | 4875 | 5947 | 5719 | 7613 | 8135 | 10610 | 7226.6878 | 7878.3956 | 7234.65 | 7894.9556 | 7617.8889 | 9373 | 99194.5778 | 5438.8889 | 5357.8889 | 5463.1067 | 5514.5348 | 5568.1598 | 5624.084 | 5753.7447 | 5818.161 | 5885.3927 | 5955.5725 | 6028.8395 | 6105.3395 | 68513.713
Returns
Comercial data
Base Value per sale | 20
Base Margin per sale | 20%
Base profits |  | BUILD Week 9: 100; BUILD Week 10: 200; BUILD Week 11: 500; BUILD Week 12: 1000; BUILD Week 13: 2000; BUILD Week 14: 5000 | 8800 | 40000 | 42000 | 44100 | 46305 | 48620.25 | 51051.2625 | 53603.8256 | 56284.0169 | 59098.2178 | 62053.1286 | 65155.7851 | 68413.5743 | 636685.0608
Scenario 1
Feature impact : Value increase | 15%
Feature impact : Margin increase | 10%
Added Profits with Personal Styles |  | BUILD Week 9: 26.5; BUILD Week 10: 53; BUILD Week 11: 132.5; BUILD Week 12: 265; BUILD Week 13: 530; BUILD Week 14: 1325 | 2332 | 10600 | 11130 | 11686.5 | 12270.825 | 12884.3662 | 13528.5846 | 14205.0138 | 14915.2645 | 15661.0277 | 16444.0791 | 17266.283 | 18129.5972 | 168721.5411
Treasury |  | -4535 | -9070 | -13945 | -19892 | -25611 | -33224 | -41359 | -51969 | -59169.1878 | -66994.5833 | -74096.7333 | -81726.6889 | -88814.5778 | -96862.5778 | -96862.5778 | -91701.4667 | -85929.3556 | -79705.9622 | -72949.672 | -65633.4656 | -57728.965 | -49277.6959 | -40180.5925 | -30404.9575 | -19916.4509 | -8679.0073 | 3345.2503 | 3345.2503
ROI 1 | [15 empty] | -97.65% | [12 empty] | 1.995%
Scenario 2
Feature impact : Value increase | 25%
Feature impact : Margin increase | 15%
Added Profits with Personal Styles |  | BUILD Week 9: 43.75; BUILD Week 10: 87.5; BUILD Week 11: 218.75; BUILD Week 12: 437.5; BUILD Week 13: 875; BUILD Week 14: 2187.5 | 3850 | 17500 | 18375 | 19293.75 | 20258.4375 | 21271.3594 | 22334.9273 | 23451.6737 | 24624.2574 | 25855.4703 | 27148.2438 | 28505.656 | 29930.9388 | 278549.7141
Treasury |  | -4535 | -9070 | -13945 | -19892 | -25611 | -33224 | -41359 | -51969 | -59151.9378 | -66942.8333 | -73958.7333 | -81416.1889 | -88159.0778 | -95344.5778 | -95344.5778 | -83283.4667 | -70266.3556 | -56435.7122 | -41691.8095 | -25988.6099 | -9277.7666 | 8420.1624 | 27226.2588 | 47196.3363 | 68389.0076 | 90865.8241 | 114691.4233 | 114691.4233
ROI 2 | [15 empty] | -96.12% | [12 empty] | 68.39%

## Project Risks
ID | Category | Risk | Title | Description | Owner | Impacts | Threats | Sources | Prevention measures | Mitigation measures | Likelihood | Severity | Criticity
1 | Scope | Feature does not satisfy user needs | Wrong scope | Users don't use the feature because they don't need it | Product Owner | - less feature usage => lower returns - users insatisfaction => less new and returning users | - users do not need this feature - users are not used to this kind of feature | - users try to use the feature | - user research during first Sprint | - users feedback/satisfaction form | 2 | 4 | 8
2 | Quality | Feature not implemented as expected by the user | Bad UX | Users don't like the feature because it does not work as they expect | UX Designer | - confused users => less feature usage and more customer support | - users do not understand how the feature works | - users try to use the feature | - A/B testing | - feature usage monitoring | 1 | 4 | 4
3 | Quality | Feature not usable because of low performances | Low performances | Users complain about latency, lag or slow results | Tech Lead | - low percieved quality => less new and returning users | - users find the feature slow | - users try to use the feature | - performance testing | - profiling => code optimization and/or infrastructure resources increase | 2 | 4 | 8
4 | Quality | Feature not usable because of low accuracy | Low accuracy | Users complain about bad recommendations | AI Engineer | - low percieved quality => less new and returning users | - users find the feature useless | - users try to use the feature | - recommendation system evaluation metric | - re-train recommender system | 4 | 4 | 16
5 | Budget | Under-estimated human costs | Greater human costs | The actual salary of contributors is much higher than estimated | Product Manager | - increased costs | - job market salaries are higher than expected | - contributors are hired / allocated to the project | - salaries benchmarking before kick-off | - re-negotiate project budget - use less paid (less skilled / more junior) contributors | 1 | 2 | 2
6 | Budget | Under-estimated infrastructure costs | Greater infrastructure costs | The actual cost of infrastructure usage is much higher than estimated | Tech Lead | - increased costs | - infrastructure price per usage increase - infrastructure usage higher than expected | - developers and AI Engineer use infrastructure resources - they don't optimize resources usage (stop unused environments) | - train tech team to resources costs optimisation | - monitor resources usage and costs | 3 | 2 | 6
7 | Budget | Over-estimated available budget | Lower budget | The actual available budget for the project is much lower than estimated | Product Manager | - not enough budget for the full project | - available budget is lower than estimated | - project budget allocation | - ask for available budget in advance | - reduce project scope | 1 | 3 | 3
8 | Planning | Under-estimated specification time | Delayed specifications | The time required to produce specification is much higher than estimated | Product Owner | - slows the production chain => delays product delivery => stretches project planning => increases costs | - product owner needs more time than estimated | - product owner prepares user stories |  | - identify and fix causes of slowness (kaizen) | 2 | 3 | 6
9 | Planning | Under-estimated feature development time | Delayed feature development | The time required to develop the feature is much higher than estimated | Tech Lead | - slows the production chain => delays product delivery => stretches project planning => increases costs | - developers needs more time than estimated | - developers develop user stories |  | - identify and fix causes of slowness (kaizen) | 3 | 2 | 6
10 | Planning | Under-estimated ML development time | Delayed ML development | The time required to train and optimize the ML models is much higher than estimated | AI Engineer | - slows the production chain => delays product delivery => stretches project planning => increases costs | - AI Engineer needs more time than estimated - data acquisition / cleaning is more complex than expected - model training / optimization is more complex than expected | - AI Engineers develop user stories |  | - identify and fix causes of slowness (kaizen) | 4 | 2 | 8
11 | Planning | Under-estimated validation time | Delayed validation | The time required to test and validate the feature is much higher than estimated | QA Engineer | - slows the production chain => delays product delivery => stretches project planning => increases costs | - QA Engineer needs more time than estimated | - QA Engineers test user stories |  | - identify and fix causes of slowness (kaizen) | 1 | 1 | 1
12 | Planning | Over-estimated available time | Premature deadline | The actual deadline of the project is much sooner than estimated | Product Manager | - not enough time for the full project | - available budget is lower than estimated | - project planning | - ask for compagny deadlines in advance | - reduce project scope | 1 | 3 | 3
13 | Team | Required skills are not available | Unavailable human resources | Persons with the required skills are not all available | Product Manager | - planning stretches => higher cost - contributors don't have the required skills => lower quality | - contributors with required skills are not available according to the planning | - project planning and human resouces allocation | - book required resources in advance | - reduce project scope - re-negotiate project budget and/or planning | 3 | 4 | 12
14 | Complexity | Identifying items in photos is harder than expected | Items identification dificulties | Developing the items recognition engine requires more resources (time, data, budget) and/or skills than estimated | AI Engineer | - planning stretches => higher cost - more infrastructure usage => higher cost - bad items detection accuracy => lower quality | - ML model is hard to train / optimize - not enough training data - bad quality training data | - AI Engineers develops items detection system | - proof of concept during first Sprint |  | 4 | 4 | 16
15 | Complexity | Making relevant recommendations is harder than expected | Recommendations dificulties | Developing the items recommendation engine requires more resources (time, data, budget) and/or skills than estimated | AI Engineer | - planning stretches => higher cost - more infrastructure usage => higher cost - bad recommender system accuracy => lower quality | - ML model is hard to train / optimize - not enough training data - bad quality training data | - AI Engineers develop recommender system | - proof of concept during first Sprint |  | 4 | 4 | 16
16 | Innovation | Integration of AI components is a first | Never done before | Since this project is the first of its kind, there is no prior knowledge ("expect the unexpected") | Product Manager | - unknown risks => high uncertainty => planning/budget/scope drift | - unknown risk | - during all the project | - integrate some margin in estimations |  | 3 | 3 | 9
17 | Compliance (PIA) | DPO and organisation manager are not defined | Undefined representatives | DPO and organisation manager must be defined | Product Manager | - not-compliant product => legal risk (> 10M€) | - record of data processing is not conform | - in case of control (CNIL / GPDP) | - identify DPO and organisation representative |  | 2 | 4 | 8
18 | Compliance (PIA) | Illegitimate access to data | Illegitimate access to data | An unauthorized entity has access to users personal data (Profile informations and/or Personal Style photos) | SRE | Profiling of data subject | - Access to the Database - Access to the Blob Storage - Man-in-the-Middle - User credentials theft | Internal human, External human, Technical incident | - SSL Encrypted communications - Software security audits and pentests - Cloud : Role Based Access Control (RBAC) - Software : Role Based Access Control (RBAC) - Blur faces - Data access and modification Traceability |  | 2 | 3 | 6
19 | Compliance (PIA) | Unwanted modification of data | Unwanted modification of data | An unauthorized entity alters users personal data (Profile informations and/or Personal Style photos) | SRE | Unusable Recommendations feature | - Access to the Database - Access to the Blob Storage - Man-in-the-Middle - User credentials theft | Internal human, External human, Technical incident | - SSL Encrypted communications - Software security audits and pentests - Cloud : Role Based Access Control (RBAC) - Software : Role Based Access Control (RBAC) - Backup and restore - Data access and modification Traceability |  | 2 | 2 | 4
20 | Compliance (PIA) | Data disappearance | Data disappearance | An unauthorized entity removes users personal data (Profile informations and/or Personal Style photos) | SRE | Unusable Recommendations feature | - Access to the Database - Access to the Blob Storage - Unavailable services - User credentials theft | Internal human, External human, Technical incident | - SSL Encrypted communications - Software security audits and pentests - Cloud : Role Based Access Control (RBAC) - Software : Role Based Access Control (RBAC) - Backup and restore - Data access and modification Traceability |  | 2 | 2 | 4
ACTION PLAN
Status | Owner | Action
TODO | AI Engineer | - proof of concept during first Sprint
TODO | AI Engineer | - recommendation system evaluation metric
TODO | Product Manager | - book required resources in advance
DONE | Product Manager | - integrate some margin in estimations
TODO | Product Owner | - user research during first Sprint
TODO | Tech Lead | - performance testing
TODO | Product Manager | - identify DPO and organisation representative
Privacy Impact Assessment (PIA)

## Processing List
Contact details | First Name | Last Name | Email Address | Phone Number | Postal Address
Responsible for the organisation | To Be Defined (TBD) | TBD | TBD | TBD | TBD
Representative | TBD | TBD | TBD | TBD | TBD
Data Protection Officer (DPO) | TBD | TBD | TBD | TBD | TBD
Processing operation | N° / REF | Date of creation of the record form | Last update of the record form | Purpose of the data processing | Special categories of personal data?
Already in place
Authentication | 1
Items search | 2
Items in shopping cart | 3
Purchase | 4
Delivery | 5
Satisfaction | 6
New
Profile settings | 7 | 2022-07-11 | 2022-07-11 | - Store user profile informations - Filter relevant items (matching profile criteria) - Improve items recommendations (content-based filtering) | No
Personal Style photos | 8 | 2022-07-11 | 2022-07-11 | - Store users Personal Styles photos - Identify relevant items (similar to those in the photo) - Improve items recommendations (content-based filtering) | No
Recommender System | 9 | 2022-07-12 | 2022-07-12 | - Produce and store items recommendations based on user Profile informations and Personal Style photos | No

## Data Processing #7 - Profile se
Description of the processing operation
Name of the processing operation | Profile settings
N° / REF | 7
Data of creation of the processing | 2022-07-11
Update of the processing | 2022-07-11
Stakeholders | Name | Address | ZIP Code | Town | Country | Phone number | Email address
Controller | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Data protection officer | TBD | TBD | TBD | TBD | TBD | TBD | TBD
DPO's Organisation (if external DPO) | N/A
Representative | N/A
Joint controller(s) | N/A
Purpose(s) of the data processing
Main purpose | Improve items recommendation
Sub-purpose 1 | Filter relevant items
Sub-purpose 2 | Store user profile informations
Sub-purpose 3 | Software debugging
Categories of personal data | Description | [5 empty] | Data retention period
Marital status, ID, identification data, images... | N/A
Personal life (lifestyle, family situation, etc.) | gender, age, shirt size, pants size, shoes size, favorite colors, favorite styles | [5 empty] | - Actual data : While consented - Backups : 2 weeks
Economic and financial information (income, financial situation, tax situation, etc.) | N/A
Connection data (IP address, logs, etc.) | N/A
Location data (movements, GPS data, GSM, etc.) | location | [5 empty] | - Actual data : While consented - Backups : 2 weeks
Social Security Number (or NIR) | N/A
Special categories of personal data | Description | [5 empty] | Data retention period
Data revealing racial or ethnic origin | N/A
Data revealing political opinions | N/A
Data revealing religious or philosophical beliefs | N/A
Data revealing trade union membership | N/A
Genetic data | N/A
Biometric data for the purpose of uniquely identifying a natural person | N/A
Data concerning health | N/A
Data concerning a natural person's sex life or sexual orientation | N/A
Data relating to criminal convictions and offences | N/A
Categories of data subjects | Description |  |  |  | Details
Category 1 | Authenticated users |  |  |  | Any user who has created an account and given their consent
Recipients | Type of recipient |  |  |  | Details
Recipient 1 | Internal - Software Engineering team |  |  |  | (Write) To store the data in the database (Read) To debug the web application
Recipient 2 | External - Cloud Service Provider |  |  |  | To host the database
Security measures | Type of security measure |  |  |  | Details
Security measure 1 | Software : Role Based Access Control (RBAC) |  |  |  | Only the user can edit its profile data
Security measure 2 | Cloud : Role Based Access Control (RBAC) |  |  |  | Only authorized internal personnel has access to the users profile data
Security measure 3 | Software security audits and pentests |  |  |  | The system is audited and pentested at least once per year
Security measure 4 | SSL Encrypted communications |  |  |  | Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel
Security measure 5 | Backup & restore |  |  |  | Daily backups stored for 2 weeks.
Security measure 6 | Data access and modification Traceability |  |  |  | Every access to and modification of data is logged : - timestamp - author_id - data_id : table_column - origin : API endpoint used - action : READ/WRITE/DELETE - new_value (if action = WRITE)
Transfers to third countries or international organisations | Recipient |  | Country |  | Type of guarantees |  | Links to relevant documents
Recipient organisation 1 | Microsoft Azure - West Europe |  | Netherlands |  | Data residency in Azure |  | Data Protection Resources

## Data Processing #8 - Personal S
Description of the processing operation
Name of the processing operation | Personal Style photos
N° / REF | 8
Data of creation of the processing | 2022-07-12
Update of the processing | 2022-07-12
Stakeholders | Name | Address | ZIP Code | Town | Country | Phone number | Email address
Controller | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Data protection officer | TBD | TBD | TBD | TBD | TBD | TBD | TBD
DPO's Organisation (if external DPO) | N/A
Representative | N/A
Joint controller(s) | N/A
Purpose(s) of the data processing
Main purpose | Improve items recommendation
Sub-purpose 1 | Identify relevant items
Sub-purpose 2 | Store user style photos and preferences
Sub-purpose 3 | Software debugging
Categories of personal data | Description | [5 empty] | Data retention period
Marital status, ID, identification data, images... | photos of people (potentially the user himself) wearing clothing items that the user likes | [5 empty] | - Actual data : While consented - Backups : 2 weeks
Personal life (lifestyle, family situation, etc.) | N/A
Economic and financial information (income, financial situation, tax situation, etc.) | N/A
Connection data (IP address, logs, etc.) | N/A
Location data (movements, GPS data, GSM, etc.) | N/A
Social Security Number (or NIR) | N/A
Special categories of personal data | Description | [5 empty] | Data retention period
Data revealing racial or ethnic origin | N/A
Data revealing political opinions | N/A
Data revealing religious or philosophical beliefs | N/A
Data revealing trade union membership | N/A
Genetic data | N/A
Biometric data for the purpose of uniquely identifying a natural person | N/A
Data concerning health | N/A
Data concerning a natural person's sex life or sexual orientation | N/A
Data relating to criminal convictions and offences | N/A
Categories of data subjects | Description |  |  |  | Details
Category 1 | Authenticated users |  |  |  | Any user who has created an account and given their consent
Category 2 | Person present in the photo |  |  |  | Any person who is the main subject or present in the background of the photo
Recipients | Type of recipient |  |  |  | Details
Recipient 1 | Internal - Software Engineering team |  |  |  | (Write) To store the photo in the blob storage (Read) To debug the web application
Recipient 2 | External - Cloud Service Provider |  |  |  | To host the blob storage
Security measures | Type of security measure |  |  |  | Details
Security measure 1 | Software : Role Based Access Control (RBAC) |  |  |  | Only the user can edit its Personal Style photos
Security measure 2 | Cloud : Role Based Access Control (RBAC) |  |  |  | Only authorized internal personnel has access to the users Personal Style photos
Security measure 3 | Software security audits and pentests |  |  |  | The system is audited and pentested at least once per year
Security measure 4 | SSL Encrypted communications |  |  |  | Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel
Security measure 5 | Backup & restore |  |  |  | Daily backups stored for 2 weeks.
Security measure 6 | Data access and modification Traceability |  |  |  | Every access to and modification of data is logged : - timestamp - author_id - data_id : table_column - origin : API endpoint used - action : READ/WRITE/DELETE - new_value (if action = WRITE)
Security measure 7 | Blur faces |  |  |  | Any detected face in photos will be blurred
Transfers to third countries or international organisations | Recipient |  | Country |  | Type of guarantees |  | Links to relevant documents
Recipient organisation 1 | Microsoft Azure - West Europe |  | Netherlands |  | Data residency in Azure |  | Data Protection Resources

## Data Processing #9 - Recommende
Description of the processing operation
Name of the processing operation | Recommender System
N° / REF | 9
Data of creation of the processing | 2022-07-12
Update of the processing | 2022-07-12
Stakeholders | Name | Address | ZIP Code | Town | Country | Phone number | Email address
Controller | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Data protection officer | TBD | TBD | TBD | TBD | TBD | TBD | TBD
DPO's Organisation (if external DPO) | N/A
Representative | N/A
Joint controller(s) | N/A
Purpose(s) of the data processing
Main purpose | Recommend relevant items to users given their Profile informations and Personal Style photos
Sub-purpose 1 | Store recommendations in database
Sub-purpose 2 | Software or recommender system debugging
Categories of personal data | Description | [5 empty] | Data retention period
Marital status, ID, identification data, images... | User items recommendations | [5 empty] | - While consented
Personal life (lifestyle, family situation, etc.) | N/A
Economic and financial information (income, financial situation, tax situation, etc.) | N/A
Connection data (IP address, logs, etc.) | N/A
Location data (movements, GPS data, GSM, etc.) | N/A
Social Security Number (or NIR) | N/A
Special categories of personal data | Description | [5 empty] | Data retention period
Data revealing racial or ethnic origin | N/A
Data revealing political opinions | N/A
Data revealing religious or philosophical beliefs | N/A
Data revealing trade union membership | N/A
Genetic data | N/A
Biometric data for the purpose of uniquely identifying a natural person | N/A
Data concerning health | N/A
Data concerning a natural person's sex life or sexual orientation | N/A
Data relating to criminal convictions and offences | N/A
Categories of data subjects | Description |  |  |  | Details
Category 1 | Authenticated users |  |  |  | Any user who has created an account and given their consent
Category 2 | Person present in the photo |  |  |  | Any person who is the main subject or present in the background of the photo
Recipients | Type of recipient |  |  |  | Details
Recipient 1 | Internal - AI Engineering team |  |  |  | (Read) To train the items detection system (Read) To train the recommender system (Read) To debug the items detection system (Read) To debug the recommender system
Recipient 2 | External - Cloud Service Provider |  |  |  | To host the recommender system processing units and store the recommendations
Security measures | Type of security measure |  |  |  | Details
Security measure 1 | Software : Role Based Access Control (RBAC) |  |  |  | Recommendations are not editable through the software
Security measure 2 | Cloud : Role Based Access Control (RBAC) |  |  |  | Only authorized internal personnel has access to the recommendations
Security measure 3 | Software security audits and pentests |  |  |  | The system is audited and pentested at least once per year
Security measure 4 | SSL Encrypted communications |  |  |  | Any communication (frontend -> backend -> database -> ML) goes through a TLS > 1.2 tunnel
Transfers to third countries or international organisations | Recipient |  | Country |  | Type of guarantees |  | Links to relevant documents
Recipient organisation 1 | Microsoft Azure - West Europe |  | Netherlands |  | Data residency in Azure |  | Data Protection Resources